## Cover Page
Customer Relationship Management
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy - Project Solutions
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Customer Relationship Management Project ID: A074 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priorities | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Login | Company CRM User | Provide system authorization to the Fraud analysis personnel | 1. Login form with sign up hyperlink below login button 2. On validating user credentials redirect to dashboard | Critical | 1 | 1
US_2 | Sign-up | Company CRM User | Save the user details in the Database and allow user login | 1. When the User clicks on the sign-up link, it should re-direct to registration form. 2. User needs to fill some of the fields as mentioned below in requirement: First Name, Last Name, DoB, Gender, Contact Number, Email ID, Job title, Company, Country, Employees (drop down listing employee count in comapany eg: 1-20, 21-200 etc) User Id, Password, Confirm password 3. Clicking ‘Submit’ should validate the datatype constraints for each field 4. User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field level validation, save the information in the database. 6. Upon saving the information in the database, display the message, ‘Your details are saved succesfully | Critical | 1 | 3
US_3 | Dashboard | Company CRM User | Dashboard should contain all links to other pages and charts displayed on dashboard screen | Dashboard homepage should contain below main and submenu links: 1. Home 2. Leads 2.1 New Lead 3. Accounts 3.1 New Account 3.2 Recent records 4.Contacts 4.1 New Contact 4.2 Recent records 5.Opportunities 5.1 New Opportunity 5.2 Recent Records 5.Cases 5.1 New case 6.Tasks 6.1 New Task 7. Calender 8. Reports | Critical | 1 | 2
US_4 | Dashboard Charts | Company CRM User | Dashboard should contain all links to other pages and charts displayed on dashboard screen | Dashboard should display chart 1.Potential Revenue Source - Current Year: display revenue generated for current year using pie chart based on category for eg: Advertisement,Employee Referral,External Referral,In-Store,Social,Other etc 2. Todays Events- List all the events added in the calender for current date 3. Todays Tasks -List all the tasks added for current date | Low
US_5 | Dashboard Event display | Company CRM User | Dashboard should display all the events set for current date | Todays Events- List all the events added in the calender for current date | Low
US_6 | Dashboard Tasks display | Company CRM User | Dashboard should display all the Tasks set for current date | Todays Tasks -List all the tasks added for current date | Low
US_7 | Leads | Company CRM User | New Lead | On click of New Lead in the submenu of Leads should open modal popup from with below fields: -Lead Information Lead Owner(Auto fetch logged in user in read only textbox) Lead Status: (Dropdown: New, Contacted, Working, Qualified, Unqualified) Name: Salutation(Dropdown: with Mr.,Ms., Mrs., Dr.,Prof.) First Name, Last Name Phone Company Email -Address Information Street City State/Province Zip/Postal Code Country Website -Additional Information No. of Employees Lead Source (Dropdown: Advertisement,Employee Referral,External Referral,In-Store,Social,Other) Annual Revenue Industry (Dropdown: Agriculture,Chemical,Biotechnology,Banking etc) -Description Information Description Save Button : Validate the fields and save details in the database | Critical | 1 | 5
US_8 | Leads | Company CRM User | Lists all leads in the gridview | On click of Lead in the main menu should open a page which lists Leads information in a gridview provided Search and export option | Medium
US_9 | Leads | Company CRM User | Import Leads | Import option should be provided above the grid and on click of the button should open the upload csv file window with the Download template given. On Upload button click should import data in the database and must refresh the grid | Low
US_10 | Accounts | Company CRM User | New Account | On click of New Account in the submenu of Accounts should open modal popup from with below fields: -Account Information Account Owner(Name of logged in user) Account Name (Entry and auto Search field for existing account) Phone Fax Website -Additional Information Type (Dropdown: Customer,Invester, Partner, Reseller ) Employees Industry (Dropdown: Agriculture,Chemical,Biotechnology,Banking etc) Annual Revenue Description Billing Address Billing Street Billing City Billing State/Province Billing Zip/Postal Code Billing Country Shipping Address Shipping Street Shipping City Shipping State/Province Shipping Zip/Postal Code Shipping Country Copy Billing Address to Shipping Address(check box on click copy address) Save Button : Validate the fields and save details in the database | Critical | 1 | 5
US_11 | Accounts | Company CRM User | Lists all accounts in the gridview | On click of Accounts in the main menu should open a page which lists Accounts information in a gridview provided Search and export option | Medium
US_12 | Accounts | Company CRM User | Import Accounts | Import option should be provided above the grid and on click of the button should open the upload csv file window with the Download template given. On Upload button click should import data in the database and must refresh the grid | Low
US_13 | Contacts | Company CRM User | Import Contacts | Import option should be provided above the grid and on click of the button should open the upload csv file window with the Download template given. On Upload button click should import data in the database and must refresh the grid | Low
US_14 | Contacts | Company CRM User | New Contact | On click of New Contact in the submenu of Contacts should open modal popup from with below fields: -Contact Information Contact Owner (Name of logged in user) Phone Name: Salutation(Dropdown: with Mr.,Ms., Mrs., Dr.,Prof.) First Name Last Name Mobile Account Name (Entry and auto Search field for existing account) Email Title Reports To (Entry and auto Search field for existing contact) -Address Information Mailing Address Mailing Street Mailing City Mailing State/Province Mailing Zip/Postal Code Mailing Country Other Address Other Street Other City Other State/Province Other Zip/Postal Code Other Country -Additional Information Fax Department Home Phone Lead Source (Dropdown: Advertisement,Employee Referral,External Referral,In-Store,Social,Other) Advertisement Other Phone Birthdate (Date Picker) Asst. Phone Assistant Description Information Description Save Button : Validate the fields and save details in the database | Medium | 2 | 5
US_15 | Contacts | Company CRM User | Lists all contacts in the gridview | On click of Accounts in the main menu should open a page which lists Accounts information in a gridview provided Search and export option | Medium | 2 | 2
US_16 | Opportunities | Company CRM User | New Opportunity | On click of New Opportunity in the submenu of Opportunity should open modal popup from with below fields: -Opportunity Information Opportunity Owner Suraj K Close Date Date Picker Opportunity Name Stage (Dropdown: Qualification,Meeting Scheduled,Proposal / Price Quote,Negotiation / Review,Closed Won,Closed Lost) Account Name (Entry and auto Search field for existing account) Probability (%) Type (Dropdown: Customer,Invester, Partner, Reseller ) Amount -Additional Information Lead Source (Dropdown: Advertisement,Employee Referral,External Referral,In-Store,Social,Other) Description Next Step Save Button : Validate the fields and save details in the database | Critical | 1 | 5
US_17 | Opportunities | Company CRM User | Import Opportunities | Import option should be provided above the grid and on click of the button should open the upload csv file window with the Download template given. On Upload button click should import data in the database and must refresh the grid | Low
US_18 | Opportunities | Company CRM User | Lists all Opportunities in the gridview | On click of Opportunities in the main menu should open a page which lists Opportunities information in a gridview provided Search and export option | Medium
US_19 | New Case | Company CRM User | Add New Case | On click of New Opportunity in the submenu of Opportunity should open modal popup from with below fields: -Case Information Case Owner Case Number(auto generated) Contact Name (User entry field with autocomplete on typing contact ) Account Name (User entry field with autocomplete on typing account) Web Email -Additional Information Status (Dropdown: New,Open, Pending, Escalated,Closed Type (Dropdown: Problem, Feature request, Question) Case Origin (Dropdown: Email,Phone,Web,Facebook,Twitter) Case Reason (Dropdown: User didn't attend training, Complex functionality, Existing problem, Instructions not clear, New problem Priority (Dropdown:Low, Medium,High,Critical) -Description Information Subject Description Internal Comments Save Button : Validate the fields and save details in the database | Critical | 2 | 5
US_20 | Cases | Company CRM User | Lists all cases in the gridview | On click of cases in the main menu should open a page which lists cases information in a gridview provided Search and export option | Medium
US_21 | Cases | Company CRM User | Import Cases | Import option should be provided above the grid and on click of the button should open the upload csv file window with the Download template given. On Upload button click should import data in the database and must refresh the grid | Low
US_22 | New Task | Company CRM User | Add New Task | On click of New Task in the submenu of Tasks should open modal popup from with below fields: -Task Information Assigned To (User entry field with autocomplete on typing exixting contact) Related To (User entry field with autocomplete on typing account) Name (User entry field with autocomplete on typing exixting contact) Subject Comments Due Date (Date Picker) -Set Task Reminder Reminder Date (Date Picker) Time(Time Picker) -Additional Information Status (Dropdown: Not started, In progress, completed, deffered, waiting for someone else) Priority (Dropdown: Normal, High, Low) Save Button : Validate the fields and save details in the database | Critical | 2 | 5
US_23 | Tasks | Company CRM User | Lists all tasks in the gridview | On click of Tasks in the main menu should open a page which lists task information in a gridview provided Search and export option | Critical | 2 | 3
US_24 | Tasks | Company CRM User | Import Tasks | Import option should be provided above the grid and on click of the button should open the upload csv file window with the Download template given. On Upload button click should import data in the database and must refresh the grid | Low
US_25 | Calender | Company CRM User | Month calender view with list of events on the date | On click of Calender in the main menu should open a page which should open whole page month calender view with events listed on the particular date | Low
US_26 | Calender | Company CRM User | Add event | User should be abe to add event on clicking on specific date Add event form should contain below fields: -Calendar Details Assigned To (User entry field with autocomplete on typing exixting contact) Related To (User entry field with autocomplete on typing account) Subject Name (User entry field with autocomplete on typing exixting contact) Start( date and time picker) End ( date and time picker) -Other Information Location -Description Information Description | Critical | 2 | 3
US_27 | Reports | Company CRM User | User should be able to generate the report | On click of Reports in the main menu should open modal popup where user has to select " Report Type" (Tasks, Accounts, Contacts, Leads, Opportunities, Cases) and on clicking "Next Button" should ask date range selection. Generate Report button should display the report in the gridview with save as excel, PDF format | Low
US_28 | Password reset / Forgot User ID | Company CRM User | As a user I should be able to reset password, retrieve User ID | 1-During registration, System should pop up three secret questions for Password recovery. 2-When the user clicks Forgot User ID, system should ask for the secret questions, contact number. On answering the questions correctly, the User ID should be displayed. 3-When the user clicks Forgot Password, system should ask for the User ID and secret questions. 4-On answering the questions correctly, the password reset page should be displayed. 5-On entering the details in the password reset page, password should be validated 6-On clicking Submit, the details should be saved to the Database | Medium
US_29 | User logout | Company CRM User | Log out from the website/ Dashboard | Logout button should be visible to the user at the top right side of the screen which on click ends user session | Critical | 2 | 2

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000